## Slide 1: R&D Capex-APPG Arbitration Gate PROCEDURE – dd/mm/yyyy
Advanced Product Planning Group

## Slide 2
 | R&D Capex-APPG Arbitration Gate |  |  | 
PROCEDURE |  |  |  | 
Reference : | Version : | Language : | Date of application : | Next revision date:
RPIFPRODT2023XXX | 1.0 | ENG | 01/05/2023 | 01/01/2025
Status : | Issuing Function: |  | Issuing Department: | 
Applicable | PRODUCT PLANNING |  | Advanced Product & Planning Group | 
Document’s subject : | This document describes the process of the R&D/Capex-APPG Arbitration gate |  | 
Associated Process : | POXX |  | 
Recipients : (Confidentiality Level) | 1-Renault Internal |  | 
 | NAME | FUNCTION | DATE and SIGNATURE
Authors : | Pierre Tcheuffa Philippe Larnaudie | APPG Process Pilot R&D/Capex Control Tower Leader | 28/04/2023
Validated by : | Maria-Eugenia Garcia-Coudoin | APPG PMO Manager | XX/04/2023
Validated by : | Benoit Bochard | VP, Group Renault Product | XX/04/2023
Approved by : | Guido Haak | Chief Advanced Product & Planning Officer | XX/04/2023
Other features (Optional) |  |  | 
To remember : | March 2023: Creation |  | 
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 3
SUMMARY
KEY PRINCIPLES & METHODOLOGY
Pages : 4-10
MILESTONE DESCRIPTION & SCOPE
Pages : 12-13
MASTER PLANNING
Page : 15
RASIC
Pages : 17-18
DELIVERABLES TIMELINE & TEMPLATE SHEET
Pages : 20-26
:
GLOSARY
Page : 28

## Slide 4
KEY PRINCIPLES & METHODOLOGY
Scope :
White Overlays : not decided projects, out of scope of Strategy Day.
Mid-Term-Plan (from budget year to 5 years spending visibility).
What :
Bi-Annual Arbitration Process
Who :
Advanced Product & Planning
Deliverable :
Official list of all Overlays and Baseline topics
Why :
Keep under control R&D and CAPEX spendings and arbitrate new funding needs for Renault Group.
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 5
KEY PRINCIPLES & METHODOLOGY
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
Why
Keep under control R&D and CAPEX spendings and arbitrate new funding needs for Renault Group.
Scope
What
Bi-Annual Arbitration Process
Who
Mid-Term-Plan (from budget year to 5 years spending visibility).
Deliverable
Advanced Product & Planning
Official list of all Overlays and Baseline topics
White Overlays : not decided projects, out of scope of Strategy Day.

## Slide 6: Background
KEY PRINCIPLES & METHODOLOGY
Fragmented decision process, with many possible gates to decide new fundings (Leadership Team Committees, Genbas, xMC, GCAC..) creating confusion on whether to start or not activities within the teams.
Difficulty to build an overall and real-time picture of R&D/Capex pile-up, including drift of decided projects. As a consequence, no visibility to assess the impact of funding decisions on overall R&D/Capex Budget.
When driving the back to budget exercises, no consideration of profitability ranking of projects or strategic APPG priorities.
    Objectives
    Keep overall R&D/Capex under control with a unique Group Control Tower.
    For all overlays out of scope of Strategy Day: put in place a new process « APPG Arbitration Gate», in order to enforce the objective of keeping under control and arbitrating budget fundings.
    Drive the back to budget exercise using new defined APPG guidelines, including a profitability ranking, and enforce offset proposals when budget is overrun.
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 7: Background
KEY PRINCIPLES & METHODOLOGY
Fragmented decision process…
Difficulty to build…
no consideration of profitability ranking...
with many possible gates to decide new fundings (Leadership Team Committees, Genbas, xMC, GCAC..) creating confusion on whether to start or not activities within the teams.
an overall and real-time picture of R&D/Capex pile-up, including drift of decided projects. As a consequence, no visibility to assess the impact of funding decisions on overall R&D/Capex Budget.
of projects or strategic APPG priorities when driving the back to budget exercises.
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 8: Objectives
KEY PRINCIPLES & METHODOLOGY
Keep overall R&D/Capex under control with a unique Group Control Tower.
For all overlays out of scope of Strategy Day: put in place a new process « APPG Arbitration Gate», in order to enforce the objective of keeping under control and arbitrating budget fundings.
Drive the back to budget exercise using new defined APPG guidelines, including a profitability ranking, and enforce offset proposals when budget is overrun.
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 9: Guidelines
KEY PRINCIPLES & METHODOLOGY
Level 2 meeting, twice a year: April and October + ad-hoc meeting if business emergency
Budget treshold : 2M€ < Topics < 100M€
Scope: All brands and all functions within the Group
Operating process description:
              APPG Control Tower launches a kickoff meeting to share the MTP Entry Ticket playground
              Stakeholders (cf RASIC page 13) gather a prioritized list of not decided topics, using the template sheet which must be completed excepted for budget R&D Capex item concerning non regulatory topics
              APPG Control Tower reviews and selects the overlay candidates to the baseline with the support of stakeholders
              APPG Control Tower prioritizes the topics based on the APPG guidelines and economic metrics
              APPG Control Tower arbitrates the overlays that will be included in the baseline
              If a gap to budget exists, APPG will drive a “back to budget” marathon to arbitrate the B* topics versus C** topics based on the A / B / C methodology (cf page 10).
1
2
4
5
3
*B : Projects before VPC w/ the best (ET/ Pma) ranking or w/ a strategic importance . C: non decided topics.
0
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 10: Guidelines
KEY PRINCIPLES & METHODOLOGY
Level 2 meeting, twice a year: April and October
+ ad-hoc meeting if business emergency
Budget treshold : 2M€ < Topics < 100M€
Scope: All brands and all functions within the Group
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 11: Guidelines
KEY PRINCIPLES & METHODOLOGY
APPG Control Tower launches a kickoff meeting to share the MTP Entry Ticket playground
Stakeholders (cf RASIC page 13) gather a prioritized list of not decided topics, using the template sheet which must be completed excepted for budget R&D Capex item concerning non regulatory topics
APPG Control Tower reviews and selects the overlay candidates to the baseline with the support of stakeholders
APPG Control Tower prioritizes the topics based on the APPG guidelines and economic metrics
APPG Control Tower arbitrates the overlays that will be included in the baseline
If a gap to budget exists, APPG will drive a “back to budget” marathon to arbitrate the B* topics versus C** topics based on the A / B / C methodology (cf page 10).
*B : Projects before VPC w/ the best (ET/ Pma) ranking or w/ a strategic importance . C: non decided topics.
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
Operating process description:
0
1
2
3
4
5

## Slide 12: Template sheet for requested project
aaa…
bbb…
Budget R&D CAPEX
Application
Project Description Abstract
Customer benefit / Cost saving / Busi. value
(1) Budget rate
Global ET (M€)
Cash in : Y/N ? From ?
PRODUCTION / SALES SECURIZATION
EXISTING PORTFOLIO CONTINUITY
OPPORTUNITY FOR ADDITIONAL
PROFIT / TURNOVER
Project title
Request for
Total additional PMa (M€) | 
Total additional Volume (Ku) | 
Custumer Value (€) / Mix | 
MSRP (K€) / Cost saving (€) | 
Total additional Turn Over (M€) | 
Start of project : date
Start of dev at the latest : date
SOS requested : date
Project Schedule
Plant UM / UCM (which one)
Family / Vehicle (which one)
Market (which one)
Other (to be specified)
Risk not to do
(qualitative answer)
(M€) | 2023 | 2024 | 2025 | Total
D&D (1) |  |  |  | 
CAPEX deliv |  |  |  | 
CAPEX cash |  |  |  | 
Context Abstract
aaa…
bbb…
Budget Owner : xxx
?
?
?
?
LCV
Project leader : xxx
?
?
Topic (white or blue) :
Overlay Selection date:
KEY PRINCIPLES & METHODOLOGY
2
1
To be documented for only Arbitration Gate milestone for non regulatory Topics
Notes: Topics
Project description + revenus (pour ce qui n’est pas réglementaire)
Priorités
Pour Overlays sélections
2024 on ne peut rien rentrer t il faut trouver 50M€, en 25 on a un peu de marge
Une liste hors réglementaire, en phase avec les priorités APPG + celles des Brands
Liste hors réglementaire hors guidelines APPG  sujet de discussion
Objectif: sortir avec une liste à chiffrer pour l’étape arbitrage
On documente le budget
Travail de convergence sur la profitabilité
On obtient ranking entre les projets
Pour Arbitration Gate
On propose les projets les plus profitables, qui rentrent dans la provision.

## Slide 13: 3 FILTERS TO PRIORITIZE WHITE OVERLAYS
FILTER 1 : APPG guidelines
Top 1. Production & Sales securization (regulation, sourcing, industrial capacity…)
Top 2. Existing portfolio continuity (baseline competitivity, attractiveness, COGS on EV,
Top 3. Opportunity for additional profit (market extension, new derivatives…)
FILTER 2 : Economic metrics
ET vs. MaP analysis (ET / MaP < 20%)
FILTER 3 : Workload R&D
Critical competences
Not applicable yet
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 14: 3 FILTERS TO PRIORITIZE WHITE OVERLAYS
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
FILTER 1 : APPG guidelines
Top 1. Production & Sales securization (regulation, sourcing, industrial capacity…)
FILTER 2 : Economic metrics
ET vs. MaP analysis (ET / MaP < 20%)
FILTER 3 : Workload R&D
Critical competences
Top 2. Existing portfolio continuity (baseline competitivity, attractiveness, COGS on EV,
Top 3. Opportunity for additional profit (market extension, new derivatives…)
NOT APPLICABLE YET

## Slide 15: FILTER 1 ZOOM : APPG 2023 GUIDELINES
1.1 PRODUCTION / SALES SECURING before portfolio continuity
    Priority 00 Europe regulatory topics (EU7, GSR2x…)
    Priority 0: Overseas regulatory topics
    Priority 1: Sourcing securing, derisking (distress suppliers…)
    Priority 2: Industrial capacity (Veh + PWT) or sales network to support existing markets
    Priority 3: Decarbonization recovery plan (CO2 bricks) + CAFx (Korea, Latam)
    Priority 3: Regional Veh Content RVC threshold per country of sales w/ significant business stakes
1.2 EXISTING PORTFOLIO CONTINUITY before opportunity for additional profit / turnover
Priority 4 : Consolidate baseline competitiveness in (EUR + LATAM)  baseline line up and PWT + Features
Priority 5 : CBU model for sales continuity in existing market (w/o increasing number of bodytypes)
Priority 5 : Styling and product content attractiveness for cost covering
Priority 6 : COGS
  EV COGS and energy savings COGS
  Blitz portfolio of COGS reduction w/ IP > 4,9 (budget capped @ 20M€ over 3y)
1.3 OPPORTUNITY FOR ADDITIONAL PROFIT / TURNOVER
Priority 7 : Model (CBU) market extension with specific specs. Visible ET/Pma  Low / Mid / Hi adaptation.
Priority 7 : New light derivative
Priority 7 : New aftersales business
Priority 8 : Others COGS reduction (Ex. RVC above threshold + Local Integration)
Note : - NO come-back on already arbitrated topics
- All request MUST comply diversity guides
- INDIA not considered
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 16: FILTER 1 ZOOM : APPG 2023 GUIDELINES
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
1.1 PRODUCTION / SALES SECURING
before portfolio continuity
Priority 00 Europe regulatory topics (EU7, GSR2x…)
Priority 0: Overseas regulatory topics
Priority 1: Sourcing securing, derisking (distress suppliers…)
Priority 2: Industrial capacity (Veh + PWT) or sales network to support existing markets
Priority 3: Decarbonization recovery plan (CO2 bricks) + CAFx (Korea, Latam)
Priority 3: Regional Veh Content RVC threshold per country of sales w/ significant business stakes
1.3 OPPORTUNITY FOR ADDITIONAL PROFIT / TURNOVER
1.2 EXISTING PORTFOLIO CONTINUITY
before opportunity for additional profit / turnover
Priority 4: Consolidate baseline competitiveness in (EUR + LATAM)  baseline line up and PWT + Features
Priority 5: CBU model for sales continuity in existing market (w/o increasing number of bodytypes)
Priority 5: Styling and product content attractiveness for cost covering
Priority 6: COGS
EV COGS and energy savings COGS
Blitz portfolio of COGS reduction w/ IP > 4,9 (budget capped @ 20M€ over 3y)
Priority 7: Model (CBU) market extension with specific specs. Visible ET/Pma  Low / Mid / Hi adaptation.
Priority 7: New light derivative
Priority 7: New aftersales business
Priority 8: Others COGS reduction (Ex. RVC above threshold + Local Integration)
- NO come-back on already arbitrated topics
- All request MUST comply diversity guides
- INDIA not considered

## Slide 17: FILTER 1 ZOOM : APPG 2023 GUIDELINES
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
1.1 PRODUCTION / SALES SECURING
before portfolio continuity
Priority 00 Europe regulatory topics (EU7, GSR2x…)
Priority 0: Overseas regulatory topics
Priority 1: Sourcing securing, derisking (distress suppliers…)
Priority 2: Industrial capacity (Veh + PWT) or sales network to support existing markets
Priority 3: Decarbonization recovery plan (CO2 bricks) + CAFx (Korea, Latam)
Priority 3: Regional Veh Content RVC threshold per country of sales w/ significant business stakes
- NO come-back on already arbitrated topics
- All request MUST comply diversity guides
- INDIA not considered

## Slide 18: FILTER 1 ZOOM : APPG 2023 GUIDELINES
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
1.2 EXISTING PORTFOLIO CONTINUITY
before opportunity for additional profit / turnover
Priority 4: Consolidate baseline competitiveness in (EUR + LATAM)  baseline line up and PWT + Features
Priority 5: CBU model for sales continuity in existing market (w/o increasing number of bodytypes)
Priority 5: Styling and product content attractiveness for cost covering
Priority 6: COGS
EV COGS and energy savings COGS
Blitz portfolio of COGS reduction w/ IP > 4,9 (budget capped @ 20M€ over 3y)
- NO come-back on already arbitrated topics
- All request MUST comply diversity guides
- INDIA not considered

## Slide 19: FILTER 1 ZOOM : APPG 2023 GUIDELINES
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
1.3 OPPORTUNITY FOR ADDITIONAL PROFIT / TURNOVER
- NO come-back on already arbitrated topics
- All request MUST comply diversity guides
- INDIA not considered

## Slide 20: FILTER 1 ZOOM : APPG 2023 GUIDELINES
KEY PRINCIPLES & METHODOLOGY
3
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
1.1 PRODUCTION / SALES SECURING
Before portfolio continuity
Priority 00: Europe regulatory topics (EU7, GSR2x…)
Priority 0: Overseas regulatory topics
Priority 1: Sourcing securing, derisking (distress suppliers…)
Priority 2: Industrial capacity (Veh + PWT) or sales network to support existing markets
Priority 3: Decarbonization recovery plan (CO2 bricks) + CAFx (Korea, Latam)
Priority 3: Regional Veh Content RVC threshold per country of sales w/ significant business stakes
1.3 OPPORTUNITY FOR ADDITIONAL PROFIT / TURNOVER
1.2 EXISTING PORTFOLIO CONTINUITY
Before opportunity for additional profit / turnover
Priority 4: Consolidate baseline competitiveness in (EUR + LATAM)  baseline line up and PWT + Features
Priority 5: CBU model for sales continuity in existing market (w/o increasing number of bodytypes)
Priority 5: Styling and product content attractiveness for cost covering
Priority 6: COGS
EV COGS and energy savings COGS
Blitz portfolio of COGS reduction w/ IP > 4,9 (budget capped @ 20M€ over 3y)
Priority 7: Model (CBU) market extension with specific specs. Visible ET/Pma  Low / Mid / Hi adaptation.
Priority 7: New light derivative
Priority 7: New aftersales business
Priority 8: Others COGS reduction (Ex. RVC above threshold + Local Integration)
- NO come-back on already arbitrated topics
- All request MUST comply diversity guides
- INDIA not considered

## Slide 21: Back to budget based on A/B/C methodology after arbitration gate
KEY PRINCIPLES & METHODOLOGY
MTP TARGET
1,578
1,961
PILE UP
1,648
1,550
2,250
2,416
A
B
C
202x Gap to target
identification
Regulatory topics + projects @ VPC or beyond
Projects before VPC w/ the best ET/ PMa ranking or with a strategic importance, up to guide level
Not decided projects: Brand life cycle management, Brands overlays, CCL development
Guiding principles
A
B
C
Chart: 
Series 1 | 4064 | 3800 | 3800
Series 2 | 264
[Units in M€]
R&D
D
D
Provision
Ranking of non-regulatory topics by ET/MaP.
Screening for new regulatory topics to be included in A tank.
Management
If gap to budget exists, need to drop one or several projects from the original B-tank in order to compensate the newly added C-topics (“marathon”)
Screening of the pile up content
Capex
PILE UP
202x
Budget 202x
w/ task 1
GAP TO TARGET
Capex
R&D
Capex
R&D
R&D
Capex
Capex
R&D
5
Cross-check non-regulatory topics priorities between APPG Guidelines and requester.
Choice of C-topics to integrate on the baseline
C
WIP
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 22
SUMMARY
KEY PRINCIPLES & METHODOLOGY
Pages : 4-10
MILESTONE DESCRIPTION & SCOPE
Pages : 12-13
MASTER PLANNING
Page : 15
RASIC
Pages : 17-18
DELIVERABLES TIMELINE & TEMPLATE SHEET
Pages : 20-26
:
GLOSARY
Page : 28

## Slide 23: Rolling Process, Twice a Year
MILESTONE DESCRIPTION & SCOPE
Propose Prioritized Topics List
Select Overlay Candidates for Baseline
PROPOSAL | CONVERGENCE | SELECTION | ARBITRATION
C
C
Overlays
Confirmation
Strategy Day
or ET > 100M€
or 2M€< ET< 100M€
APPG
Arbitration
Gate
C : Projects not decided
Baseline decision
Baseline decision
Blue topics with ET > 100M€
White topics with ET < 100M€
White +blue
topics
Level1
Level2
Level3
Controlling
PPL
PDL
Engineering
Topics
APPG
Marathon back to budget guide
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 24: Rolling Process, Twice a Year
MILESTONE DESCRIPTION & SCOPE
Propose Prioritized Topics List
Select Overlay Candidates for Baseline
C
C
Overlays
Confirmation
Strategy Day
or ET > 100M€
or 2M€< ET< 100M€
APPG
Arbitration
Gate
C : Projects not decided
Baseline decision
Baseline decision
Blue topics with ET > 100M€
White topics with ET < 100M€
White +blue topics
Level1
Level2
Level3
Topics
APPG
Marathon back to budget guide
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
PROPOSAL
CONVERGENCE
SELECTION
ARBITRATION
PPL
PDL
Engineering
controlling

## Slide 25: A unique matrix to sort topics to be addressed in #1 Strategy Day or in #2 APPG Arbitration Gate
MILESTONE DESCRIPTION & SCOPE
or Topic w/ TE > 100M€
 Strategy Day (Level 1)
or Topic w/ TE < 100M€
 APPG Arbitration Gate (Level 2)
Vehicle | Regional Brand footprint | D3 / D5 | D2 |  | D0/ D1 | Collection | Extension market
Platform | New | Heavy modif | Light modif |  | Carry over |  | 
Sweet / CCS | Sweet Main | New generation | New minor domain variante |  | Re-use of existing variante |  | 
PWT incl. Battery | Regional techno strategy | New PWT family or generation | PWT variant on new platform |  | PWT adaptation on same platform | Carry over pack | 
Industrial | Footprint | Green & brownfield | Plant heavy modif | Plant heavy modif | Single shop heavy or plant med. modif | Plant or shop modif | 
Regulatory step | Stop | Apply |  |  |  |  | 
Sales / RRG | Footprint | Real Estate | Big project |  | Retrofit | Run | 
Refactory / Ecosystem | Footprint | Retrofit | Re-energy |  | Restart | Recycle | 
Other cost engineering | Big invest engineering | Distress Supplier | R&AE Innovation |  |  |  | 
Aftersales | Qstomize refactory greenfield | Warehouse modif |  |  |  |  | 
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 26
SUMMARY
KEY PRINCIPLES & METHODOLOGY
Pages : 4-10
MILESTONE DESCRIPTION & SCOPE
Pages : 12-13
MASTER PLANNING
Page : 15
RASIC
Pages : 17-18
DELIVERABLES TIMELINE & TEMPLATE SHEET
Pages : 20-26
:
GLOSARY
Page : 28

## Slide 27: 202x TIMETABLE
MASTER PLANNING
CONTROL TOWER
ARBITRATION
PREPARATION
Overlays
confirmation
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Topics
START LOOP 1
START LOOP 2
Visibility R&D CAPEX
(REP3)
Visibility R&D CAPEX
(REP9)
Overlays
confirmation
APPG Arbitration Gate
White topics
Blue topics
Strategy day
Topics
Strategy day
Blue topics
APPG Arbitration Gate
White topics
Level1
Level2
Level3
APPG
Marathon back to budget guide
APPG
Marathon back to budget guide
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
Notes: Topics = Kick-off
Donner les Guidelines
Donner le niveau de dépassement budgétaire.
Avoir en input avant le kick-off:
Réglementaires (documentation coûts, timeline)
Principaux évènements d’animation line-up (requests avec leurs revenus)

## Slide 28: 202x TIMETABLE
MASTER PLANNING
CONTROL TOWER
ARBITRATION
PREPARATION
Overlays
confirmation
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Topics
START LOOP 1
START LOOP 2
Visibility R&D CAPEX
(REP3)
Visibility R&D CAPEX
(REP9)
Overlays
confirmation
APPG Arbitration Gate
White topics
Blue topics
Strategy day
Topics
Strategy day
Blue topics
APPG Arbitration Gate
White topics
Level1
Level2
Level3
APPG
Marathon back to budget guide
APPG
Marathon back to budget guide
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023
Notes: Topics = Kick-off
Donner les Guidelines
Donner le niveau de dépassement budgétaire.
Avoir en input avant le kick-off:
Réglementaires (documentation coûts, timeline)
Principaux évènements d’animation line-up (requests avec leurs revenus)

## Slide 29
SUMMARY
KEY PRINCIPLES & METHODOLOGY
Pages : 4-10
MILESTONE DESCRIPTION & SCOPE
Pages : 12-13
MASTER PLANNING
Page : 15
RASIC
Pages : 17-18
DELIVERABLES TIMELINE & TEMPLATE SHEET
Pages : 20-26
:
GLOSARY
Page : 28

## Slide 30: Responsability split
RASIC
 | Function /Brand Perimeter** | DPV Volumes | APPG | PPL Brand*/ CCL* | Budget owner | Engineering Product/ Process* | DPCIP
Kickoff meeting to share the MTP Entry Ticket playground | All | I | A/R | I | I | I | I
Gather new list of Topics to be financed | Line up | S |  | A | R | S | 
 | Non-line-up | S |  |  | A/R | S | 
 | Non- industrial | S |  | - | A/R | - | 
Documente the new topics for financing (fill the template APPG Arbitration gate w/o R&D Capex figures for non regulatory topics until the APPG Arbitration Gate milestone | Line up & Non-Line up | S | I | A/R | - | S | S
 | Non-Industrial | S | I | - | A/R | - | S
Review the template sheet with the pilot to assess the relevance of the request and its documentation | All | - | A/R | S | S | S | S
Overlay Projects selections for arbitration gate | All | I | A/R | I | I | I | I
Projects Ranking based on APPG priorities guidelines and profitability assessment | All |  | A/R |  |  |  | S
Decision to integrate project into the Baseline including funding agreement | All | I | A/R | S | S |  | S
Propose and arbitrate compensations solutions for line-up to offset the finance agreed new requests | All | I | A | R | S | S | I
Integrate in MTP R&D/Capex the decisions of the Arbitration gate | ALL |  | S | S | S |  | A/R
R Responsible (carries out the activity) - A Accountable & Approval authority -
S Support (contributes to the activity) - Informed (not involved in final decision-making) - C Consulted (involved in final decision-making)
*: RASIC Columns applied only for industrial Line up & non line-up topics
**: Cf List of the Functions/Brand Perimeter next page

## Slide 31: Responsability split
RASIC
 | Function /Brand Perimeter** | DPV Volumes | APPG | PPL Brand*/ CCL* | Budget owner | Engineering Product/ Process* | DPCIP
Kickoff meeting to share the MTP Entry Ticket playground | All | I | A/R | I | I | I | I
Gather new list of Topics to be financed | Line up | S |  | A | R | S | 
 | Non-line-up | S |  |  | A/R | S | 
 | Non- industrial | S |  | - | A/R | - | 
Documente the new topics for financing (fill the template APPG Arbitration gate w/o R&D Capex figures for non regulatory topics until the APPG Arbitration Gate milestone | Line up & Non-Line up | S | I | A/R | - | S | S
 | Non-Industrial | S | I | - | A/R | - | S
Review the template sheet with the pilot to assess the relevance of the request and its documentation | All | - | A/R | S | S | S | S
Overlay Projects selections for arbitration gate | All | I | A/R | I | I | I | I
Projects Ranking based on APPG priorities guidelines and profitability assessment | All |  | A/R |  |  |  | S
Decision to integrate project into the Baseline including funding agreement | All | I | A/R | S | S |  | S
Propose and arbitrate compensations solutions for line-up to offset the finance agreed new requests | All | I | A | R | S | S | I
Integrate in MTP R&D/Capex the decisions of the Arbitration gate | ALL |  | S | S | S |  | A/R
R Responsible (carries out the activity) - A Accountable & Approval authority - S Support (contributes to the activity) - Informed (not involved in final decision-making) - C Consulted (involved in final decision-making)
*: RASIC Columns applied only for industrial Line up & non line-up topics
**: Cf List of the Functions/Brand Perimeter next page

## Slide 32: List of Budget Owners
RASIC
Functions/Brand | *Budget owner
Dacia | Dacia brand Engineering Dir
Renault VP | Renault brand Engineering Dir
Renault VP international | Dacia brand Engineering Dir
Renault VP RKM | RKM Engineering Dir
LCV / FlexEVan | LCV Engineering Dir
Alpine | Alpine brand CEO
Mobilize | Mobilize brand CEO
Modules | VP, Platforms &Modules
Platforms | VP, Platforms &Modules
Sweet / CCS | EE/Systems Engineering Dir/APP
PWT | PWT Engineering Dir/PWT Process Engineering Dir
VEH Non Lineup | Process Engineering Dir
Manufacturing | Industrial Strategy & Process Engineering Dir
RRG | RG Commercial dept Dir
Retail Renault | Renault Brand COE
Retail Dacia | Dacia Brand Mktg, S&Op Dir
IS / IT | IT &Digital Dir
Future is neutral | Refactory& Circular Eco Dir
E&D | Test/Client perf CAE Dir
Design | Chief Design Officer
DLPA | RG Global After Sales Dir
Other Eng Cost | 
SET & Distressed suppliers | Chief Purchasing Officer
Line-up | Chief Advanced Product Planning Officer
Cash in partners | Chief Advanced Product Planning Officer
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 33: List of Budget Owners
RASIC
Functions/Brand | *Budget owner
Dacia | Dacia brand Engineering Dir
Renault VP | Renault brand Engineering Dir
Renault VP international | Dacia brand Engineering Dir
Renault VP RKM | RKM Engineering Dir
LCV / FlexEVan | LCV Engineering Dir
Alpine | Alpine brand CEO
Mobilize | Mobilize brand CEO
Modules | VP, Platforms &Modules
Platforms | VP, Platforms &Modules
Sweet / CCS | EE/Systems Engineering Dir/APP
PWT | PWT Engineering Dir/PWT Process Engineering Dir
VEH Non Lineup | Process Engineering Dir
Manufacturing | Industrial Strategy & Process Engineering Dir
RRG | RG Commercial dept Dir
Retail Renault | Renault Brand COE
Retail Dacia | Dacia Brand Mktg, S&Op Dir
IS / IT | IT &Digital Dir
Future is neutral | Refactory& Circular Eco Dir
E&D | Test/Client perf CAE Dir
Design | Chief Design Officer
DLPA | RG Global After Sales Dir
Other Eng Cost | 
SET & Distressed suppliers | Chief Purchasing Officer
Line-up | Chief Advanced Product Planning Officer
Cash in partners | Chief Advanced Product Planning Officer
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 34
SUMMARY
KEY PRINCIPLES & METHODOLOGY
Pages : 4-10
MILESTONE DESCRIPTION & SCOPE
Pages : 12-13
MASTER PLANNING
Page : 15
RASIC
Pages : 17-18
DELIVERABLES TIMELINE & TEMPLATE SHEET
Pages : 20-26
:
GLOSARY
Page : 28

## Slide 35
DELIVERABLES PER MILESTONE
INPUTS AND DELIVERABLES
overlays
confirmation
Jan
Feb
Mar
Apr
May
Jun
Jul
Aug
Sep
Oct
Nov
Dec
Level3
START LOOP 1
START LOOP 2
APPG Arbitration Gate
White topics
Blue topics
Strategy day
(1) : TE < 100M€ - (2) : > 100M€
White topics
Level1
Level2
Strategy day
APPG Arbitration Gate
APPG
Marathon back to budget guide
overlays
confirmation
APPG Arbitration Gate
APPG
Marathon back to budget guide
Strategy day
Blue topics

## Slide 36
Chart: 
| NON LINE-UP | LINE-UP | REGUL
 | 0.28125 | 0.63542 | 0.083333
AFTER CONVERGENCE : XXX « C-TOPICS » proposed as overlay
To be decided and financed
NON LINE-UP
REGULATORY
LINE-UP
Chart: 
| EXISTING PORTFOLIO CONTINUITY | PRODUCTION / SALES SECURIZATION | OPPORTUNITY FOR ADDITIONAL PROFIT
Ventes | 25 | 34 | 37
XXXX
REGULATORY
LINE-UP (w/o regulatory)
NON LINE-UP (w/o regulatory)
TOTAL | 
RENAULT | 
LCV incl. FLEXIS | 
DACIA | 
INDUST Veh + PWT | 
RKM | 
MOBILIZE | 
ALPINE | 
CCL | 
TOTAL | xx
RENAULT | 
LCV incl. FLEXIS | 
DACIA | 
ALPINE | 
RKM | 
MOBILIZE | 
ALL BRANDS (Blitz) | 
CCL | 
TOTAL | 
Manuf. Veh | 
Manuf. PWT | 
DLPA | 
IS/IT | 
Sample sheet

## Slide 37
BRAND | WHAT | SOS | PRIORITY | RATIONALE | APPG PROPOSAL
RENAULT | xxx | xxx | xxx | xxx | OVERLAY
DACIA | xxx | xxx | xxx | xxx | OVERLAY
LCV | xxx | xxx | xxx | xxx | OVERLAY
REGULATORY
Overlay candidates to Baseline
Sample sheet
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 38
BRAND | WHAT | SOS | PRIORITY | RATIONALE | APPG PROPOSAL
RENAULT | XXX | XXX | XXX | XXX | OVERLAY
DACIA | XXX | XXX | XXX | XXX | OVERLAY
ALPINE | XXX | XXX | XXX | XXX | OVERLAY
LINE-UP / BRAND
Overlay candidates to Baseline before filtering
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 39
BRAND | WHAT | SOS | PRIORITY | RATIONALE
ALPINE | xxx | xxx | xxx | xxx
RENAULT | xxx | xxx | xxx | xxx
DACIA | xxx | xxx | xxx | xxx
LINE-UP / NLU
Topics for which the framing needs to be rediscussed
Sample sheet
RPIF APPG R&D/CAPEX ARBITRATION GATE March 2023

## Slide 40
BRAND | WHAT | SOS | PRIORITY | RATIONALE | APPG PROPOSAL
RENAULT | XXX |  |  |  | Budget MVS
PF | XXX |  |  |  | Budget MVS
PWT | XXX |  |  |  | Budget MVS
LINE-UP
Topics to be financed in MVS budget

## Slide 41
SUMMARY
KEY PRINCIPLES & METHODOLOGY
Pages : 4-10
MILESTONE DESCRIPTION & SCOPE
Pages : 12-13
MASTER PLANNING
Page : 15
RASIC
Pages : 17-18
DELIVERABLES TIMELINE & TEMPLATE SHEET
Pages : 20-26
:
GLOSARY
Page : 28

## Slide 42
GLOSSARY
ACRONYME | 
RPIF | Regles, Processus, Instructions et Formulaires
APPG | Advanced Product & Planning Group
xMC | X Brand Management Committee
GCAC | Group Capex and Allocation Committee
PPL | Product Performance Leader
PDL | Product Development Leader
CCL | Cross Car Line
CAPEX | Capital expenditure
ET | Entry Ticket
MaP | Marginal Profit
REPx | Reprevision on x month

## Slide 43
THANKS

## Slide 44: Template sheet for requested project
aaa…
bbb…
Budget R&D CAPEX
Application
Project Description Abstract
Customer benefit / Cost saving / Busi. value
(1) Budget rate
Global ET (M€)
Cash in : Y/N ? From ?
PRODUCTION / SALES SECURIZATION
EXISTING PORTFOLIO CONTINUITY
OPPORTUNITY FOR ADDITIONAL
PROFIT / TURNOVER
Project title
Request for
Total additional PMa (M€) | 
Total additional Volume (Ku) | 
Custumer Value (€) / Mix | 
MSRP (K€) / Cost saving (€) | 
Total additional Turn Over (M€) | 
Start of project : date
Start of dev at the latest : date
SOS requested : date
Project Schedule
Plant UM / UCM (which one)
Family / Vehicle (which one)
Market (which one)
Other (to be specified)
Risk not to do
(qualitative answer)
(M€) | 2023 | 2024 | 2025 | Total
D&D (1) |  |  |  | 
CAPEX deliv |  |  |  | 
CAPEX cash |  |  |  | 
Context Abstract
aaa…
bbb…
Budget Owner : xxx
?
?
?
?
LCV
Project leader : xxx
?
?
Topic (white or blue) :
Overlay Selection date:
KEY PRINCIPLES & METHODOLOGY
2
1
Notes: Topics
Project description + revenus (pour ce qui n’est pas réglementaire)
Priorités
Pour Overlays sélections
2024 on ne peut rien rentrer t il faut trouver 50M€, en 25 on a un peu de marge
Une liste hors réglementaire, en phase avec les priorités APPG + celles des Brands
Liste hors réglementaire hors guidelines APPG  sujet de discussion
Objectif: sortir avec une liste à chiffrer pour l’étape arbitrage